## Time Log
Date | Day | Estimated Hours | Sessions | Commits | Cumulative Hours | Work Summary
2026-05-19 | Tuesday | 0.5 | 1 | 2 | 0.5 | Repository created ("first commit") and the pre-existing legacy codebase uploaded in bulk via GitHub's 'Add files via upload' flow. Not new development in this tracked history -- superseded three weeks later by the 2026-06-09 rewrite, which the project treats as the real initial commit.
2026-06-09 | Tuesday | 0.7 | 1 | 2 | 1.2 | True project baseline. 'Initial commit' establishes ZeroBreach V23 'Kraken Console' -- the PowerShell scan engine plus the cyberpunk HTML/JS frontend (themes, sound, VFX, kraken cinematic) -- as the current tree. Followed by a merge folding in the old 2026-05-19 upload history so the legacy files stop conflicting with it.
2026-06-16 | Tuesday | 0.8 | 1 | 2 | 2 | Housekeeping day. Created local Claude Code working files for the assistant to use across sessions, and pulled in a raw automated session dump captured from a separate 'work rig' machine -- research/detection material that later sessions mined for WS1/WS2 signature content.
2026-06-22 | Monday | 4 | 1 | 4 | 6 | First real detection-engineering day. Added email attachment phishing/trojan detection (Phase 74.5, scoped to Outlook attachment caches, not the multi-GB OST); bounded the recursive file-walk scans and added a proactive-hardening deployment policy; cut WMI query storms and deferred multi-minute repair operations behind a new error trap; merged all of that quarantine-branch work (perf + WMI optimization + phishing detection) into main.
2026-06-23 | Tuesday | 8.5 | 3 | 18 | 14.5 | The biggest day of the project, three separate sessions. Early morning: fixed Authenticode signature-check hangs (unbounded CRL/OCSP revocation lookups blocking the scan), general output floods, and a UI freeze; fixed a PowerShell 5.1 bug where (try{}catch{}) used as an expression silently disabled Phases 44 and 69. Late morning through evening, the long stretch: added bespoke per-theme canvas backgrounds and a per-view FX layer; built an FX visual-audit harness/checker; wired MITRE ATT&CK tagging, the IOC Manager, HTML/CSV export, STEALTH-mode parsing, and real remediation end-to-end; documented the benign remediation test tripwires; built the two-layer remediation safety guard (hard-block on protected/system-critical resources, then a frontend Layer 2 plus a completion-modal count fix); added trusted-vendor handling for Datto/CentraStage/Kaseya RMM partner tooling; shipped opt-in cinematic FX toggles plus boot self-heal; ran FP-tuning rounds 1 and 2 (cert/cloaked/info-stealer over-matchers, then SafeBoot and named-pipe CRITICAL floods). Late night: FP-tuning round 3 (Hidden Tasks and BITS HIGH floods downgraded to non-destructive). HANDOFF.md was updated repeatedly throughout to record progress between sessions.
2026-06-25 | Thursday | 0.5 | 1 | 1 | 15 | Fixed live DEEP-run noise and the real Phase-68 credential-flood bug in the engine -- a Get-ScanFiles piping issue that was matching far more files than intended.
2026-06-26 | Friday | 0.9 | 1 | 4 | 15.9 | FP-tuning round 4: killed 7 live auto-destructive false-positive floods plus a PowerShell 5.1 Get-Sig string-indexing bug (a single-element array silently unwraps to a string, so [0] indexed its first character). Round 4b followed immediately: fixed Phases 32 and 66 so the engine never auto-deletes developer-tool DLLs or the user's own executables. Documented the round (auto-destructive findings down from 319 to 75, validated on 3 live DEEP runs) and logged a HANDOFF to triage the remaining 75.
2026-06-28 | Sunday | 2.2 | 1 | 6 | 18.1 | FP-tuning round 5, the biggest safety fix of the project: killed a Phase-108 icacls C:\ /reset /T command that would reset ACLs across the entire C: drive on any healthy machine, plus its ACL-cluster sibling phases. Recorded the commit, then re-graded a live -Hours 0 run (auto-destructive findings down to 52, confirmed the Phase-29 fix held). Shipped durable per-run server logs and made scan_state fire on every phase change instead of a throttled tick, fixing the UI's apparent 'skipped phases' symptom. Wrote a next-steps runbook for the still-open live GUI validation.
2026-06-29 | Monday | 0.5 | 1 | 1 | 18.6 | Docs-only day: confirmed session-2's work (durable logs plus the phase-skip display fix) was pushed to origin.
2026-07-01 | Wednesday | 1.8 | 2 | 10 | 20.4 | Consolidated all standing rules into CLAUDE.md and started CHANGELOG.md for bug-fix history (early session). That evening: the engine split -- rewrote ZeroBreach-V23.ps1 from one monolithic script into a thin loader plus dot-sourced engine/Phases-1/2/3.ps1 modules -- merged in WS1/WS2 detection research from a separate work-rig branch, ported those WS2 detections into the new split modules (all graded FixAction Info, non-destructive), and added a module-level resilience trap to each phase module after finding the split had a trap-scoping bug that could silently skip whole phase ranges. Fixed a Phase 53 false positive (generic ransom-note filenames now need content confirmation before delete). Documented the new split architecture and logged a session-4 handoff.
2026-07-02 | Thursday | 6.1 | 3 | 14 | 26.5 | Started just after midnight recording that the first live GUI DEEP run passed all 115 phases with 0 errors. Then found and fixed why the live finding stream had gone dead: a case-insensitive $sev/$SEV variable shadow that had silently disabled severity classification, plus a UTF-8 stdout pipeline bug causing mojibake in the console banners. Wrote BLUEPRINT.md as the new product map, superseding the old planning docs. Built a portable release zip with Mark-of-the-Web self-unblocking, and made the server's phase counter track fractional phases (55.5, 74.5-.7, 99.5) as real plan steps instead of rounding them away. Mid-afternoon: an additional commit landed more Claude Code changes. That evening: FP-tuning round 6 (cleared the remaining healthy-box auto-destructive tail); shipped scan profiles (save/apply named scan configurations) and fixed a bug where a malformed JSON POST body would hang the client with no response, across every route; regenerated the coverage-matrix audit against the new split engine; wired up 15 signature keys that had been sitting unused in the data file.
2026-07-03 | Friday | 0.5 | 1 | 2 | 27 | Made QUICK mode a real enforced 30-phase gate instead of just a label. Fixed a latent rootkit-detection bug where a local $pid variable was clobbering PowerShell's automatic $PID variable -- the same class of case-insensitive shadow bug as the $SEV one from two days earlier.
Total

## Quick View
Date | Day | Hours
2026-05-19 | Tuesday | 0.5
2026-06-09 | Tuesday | 0.7
2026-06-16 | Tuesday | 0.8
2026-06-22 | Monday | 4
2026-06-23 | Tuesday | 8.5
2026-06-25 | Thursday | 0.5
2026-06-26 | Friday | 0.9
2026-06-28 | Sunday | 2.2
2026-06-29 | Monday | 0.5
2026-07-01 | Wednesday | 1.8
2026-07-02 | Thursday | 6.1
2026-07-03 | Friday | 0.5
Total